## Slide 1: PUTTING PUBLIC HEALTH EVIDENCE IN ACTION
This training is supported by the Centers for Disease Control and Prevention of the U.S. Department of Health and Human Services (HHS) as part of financial assistance awards (cooperative agreement numbers U48 DP006400 and U48 DP006377). The contents are those of the author(s) and do not necessarily represent the official views of, nor an endorsement, by CDC/HHS, or the U.S. Government.
Implement Evidence-Based Interventions

## Slide 2
Understand problem
Establish goals for improvement
Find and Select EBIs
Adapt EBIs
Implement EBIs
Evaluate impact
Engage Stakeholders
EBI = Evidence-Based Intervention

## Slide 3: Objectives
Describe six steps to successful implementation
Assess a setting’s readiness to implement an EBI
Develop an implementation plan
Conduct a Plan-Do-Study-Act cycle
Use communication strategies to engage key stakeholders

## Slide 4: Definition of implementation
Implementation is a specified set of activities designed to integrate an intervention into a routine practice setting and sustain it over time.
Adapted from National Implementation Research Network (nirn.fpg.unc.edu)

## Slide 5: Why implementation is important
Interventions need to be effective, and to
Reach intended patients and populations
Be adopted by providers and practice settings
Be implemented with fidelity (i.e., as designed)
And be maintained over time
(RE-AIM.org)

## Slide 6
Effective Intervention
Successful Implementation
Positive Outcomes
The importance of implementation

## Slide 7: Steps for Effective Implementation
1. Establish an implementation team
4. Create an implementation plan
5. Conduct Plan Do Study Act (PDSA) cycles
2. Assess your readiness to implement
6. Communicate with key stakeholders
3. Select implementation strategies

## Slide 8: 1. Establish an implementation team
Implementation teams are key to
Planning how to implement
Strategizing how to overcome barriers
Generating support for the EBI
Monitoring and improving implementation over time

## Slide 9: How to establish an implementation team
Decide who will convene the team
Identify who will be on the team
Agree on when the team will meet
Record team progress and decisions

## Slide 10
Handout #1

## Slide 11: Aim Statement and Measurable Objectives
Aim Statement: Increase colorectal cancer screening rates through high quality implementation of the evidence-based Flu FIT Program.
Measurable Objectives
Provide a FIT testing kit and recommendation to at least 80% of patients who participate in the September 2021 FLU clinic and are due for colorectal screening.
At least 75% of patients who receive a kit will return the kit by December 30, 2021.
100% of patients with positive results will get follow-up diagnostic testing.

## Slide 12: Team Members for Flu-FIT Program
Team Members
- Team Lead Quality Improvement Specialist
- Team Recorder Clinic manager
- Other members of team Clinic nurse and medical assistant
Team Meeting Schedule and Location
12 noon on second Tuesday of each month in conference room 1.

## Slide 13
Handout #1

## Slide 14: Steps for Effective Implementation
1. Establish an implementation team
4. Create an implementation plan
5. Conduct Plan Do Study Act (PDSA) cycles
2. Assess your readiness to implement
6. Communicate with key stakeholders
3. Select implementation strategies

## Slide 15: To assess readiness
Create a process flow diagram to identify who will need to do what and when to deliver the intervention (revisit module 2 for guidance on process flow diagrams)
Complete an organizational readiness checklist

## Slide 16: Complete an organizational readiness checklist (Handout #2)
Does leadership support the intervention?
Have we identified staff to deliver the intervention?
Do we have plans for educating & supporting staff?
What space, equipment, and materials are needed?
Do we have a plan for recruiting patients?

## Slide 17: Gaps in readiness for Flu FIT Program Implementation
1. Leadership support
2. Develop a plan for educating and supporting staff
3. Develop a plan for recruiting patients

## Slide 18: Steps for Effective Implementation
1. Establish an implementation team
4. Create an implementation plan
5. Conduct Plan Do Study Act (PDSA) cycles
2. Assess your readiness to implement
6. Communicate with key stakeholders
3. Select implementation strategies

## Slide 19: Implementation strategies are
Specific methods or techniques that can be used to
Prepare to implement an intervention
Implement an intervention into routine practice
Maintain an intervention over time
Handout #3

## Slide 20: Examples of implementation strategies
Change physical structure and equipment
Change record systems
Conduct ongoing training
Distribute educational materials
Identify and prepare champions
Remind clinicians
Powell et al., 2015

## Slide 21: Selecting strategies to address gaps in readiness for Flu/FIT Program Implementation
Develop a plan for educating & supporting staff
- Conduct an educational meeting
- Develop and distribute educational materials
- Remind clinicians

## Slide 22: Steps for Effective Implementation
1. Establish an implementation team
4. Create an implementation plan
5. Conduct Plan Do Study Act (PDSA) cycles
2. Assess your readiness to implement
6. Communicate with key stakeholders
3. Select implementation strategies

## Slide 23: To identify the tasks to include in the implementation plan
Review your aims and objectives
Review information about the EBIs
Review your process diagram
Assess your readiness to implement
Consider your implementation strategies
Notes: Talking Points:
•A work plan can be developed by considering the
•original program materials,
•readiness assessment,
•selection, and
•adaptation tools.
•Ideas about adaptation should be incorporated in the work plan.

## Slide 24: To create an implementation plan
Make a list of the specific tasks that need to be completed
Create a timeline for when tasks will be completed
Designate the individual who will be responsible for each task
See Handout # 4 for template

## Slide 25: Partial Implementation Plan: Flu FIT
Actions | Due date | Person Responsible
Pre-implementation |  | 
Create system to flag patients due for screening in EHR | April 2021 | IT
Purchase FIT kits | July 2021 | Clinic manager
Develop and pilot test FIT kit instructional materials | July 2021 | QI specialist
Create and pilot a log for tracking FIT kit distribution/return | August 2021 | Clinic manager
Train staff on new Flu FIT program | August 2021 | Clinic nurse
Implementation |  | 
Send MyChart message to all eligible patients | August 2021 | Clinic manager and IT

## Slide 26: Steps for Effective Implementation
1. Establish an implementation team
4. Create an implementation plan
5. Conduct Plan Do Study Act (PDSA) cycles
2. Assess your readiness to implement
6. Communicate with key stakeholders
3. Select implementation strategies

## Slide 27
Conduct PDSA Cycles
Use the PDSA cycle to test changes and organize feedback
See handout #5 for a template

## Slide 28
Why Use PDSA Cycles?
Helps adapt good ideas to your specific situation:
  Forces us to think small
  Forces us to be methodical, make predictions and learn
  Allows rapid adaptation & implementation of changes

## Slide 29
Steps in PDSA Cycle | Example of solution to getting to work late
Plan a possible solution | Lay out your clothes the night before
Do the solution on a small scale | Try it for one week
Study whether it worked | Track arrival time at work on a calendar
Act by enacting the solution more widely | If it worked, make it your permanent practice.

## Slide 30: Rapid Cycles of Change
A
P
S
D
A
P
S
D
A
P
S
D
D
S
P
A
Learning
Changes That Result in Improvement
Hunches Theories Ideas

## Slide 31: PDSA Cycles During Pre-implementation
Actions | Due date | Person Responsible
Pre-implementation |  | 
Create system to flag patients due for screening in EHR | April 2021 | IT
Purchase FIT kits | July 2021 | Clinic manager
Develop and pilot test FIT kit instructional materials | July 2021 | QI specialist
Create and pilot a log for tracking FIT kit distribution/return | August 2021 | Clinic manager
Train staff on new Flu FIT program | August 2021 | Clinic nurse
Implementation |  | 
Send MyChart message to all eligible patients | August 2021 | Clinic manager and IT

## Slide 32
Steps in PDSA Cycle | Pilot Test of FIT kit instructional materials
Plan what you will pilot | A one-page sheet designed for low literacy
Do the solution on a small scale | Try it for one week with one provider's patients
Study whether it worked | After patients review sheet, ask them to explain how they will use the FIT kit.
Act by enacting the solution more widely | If it worked, make it your permanent practice. If not, improve and test again

## Slide 33: PDSA Cycles During Implementation & Maintenance
Monitor implementation and identify gaps
Explore possible causes of implementation gaps
Test solutions to address those causes and improve implementation (PDSA cycles)

## Slide 34: Possible causes of implementation gaps
Characteristics of the Intervention
Outer Setting
Inner Setting
Individuals
Implementation Processes
The Consolidated Framework for Implementation Research (CFIR) categorizes factors that affect implementation within five domains.
Damschroder et al. (2009)
Damschroder et al. (2009)

## Slide 35: Activity
Retrieve Handout #6: List of CFIR constructs and Handout #7: Flu FIT Case Study
Brainstorm factors that might be barriers (or facilitators) to implementing Flu FIT
Try to identify at least one factor within each of the five CFIR domains.

## Slide 36: Examples of potential barriers
Intervention characteristics
  Intervention source
Outer setting
  Patient needs and resources
Inner setting
  Relative priority
Characteristics of individuals
  Knowledge of the intervention
Process
  Planning
  Engaging

## Slide 37: The list of implementation strategies may suggest ways to overcome barriers
Change physical structure and equipment
Change record systems
Conduct ongoing training
Distribute educational materials
Identify and prepare champions
Remind clinicians
Powell et al., 2015

## Slide 38: Steps for Effective Implementation
1. Establish an implementation team
4. Create an implementation plan
5. Conduct Plan Do Study Act (PDSA) cycles
2. Assess your readiness to implement
6. Communicate with key stakeholders
3. Select implementation strategies

## Slide 39: Communicate with key stakeholders
Engaged stakeholders prevent program drift –
  When energy and attention shifts to the next new intervention or the latest crisis, and the quality of intervention delivery diminishes over time.
Communication is essential to keeping key stakeholders engaged!

## Slide 40: Who are the key stakeholders for your Flu-FIT Program?
  Leadership who will promote and support Flu-FIT
  Healthcare providers who will refer their patients to Flu-FIT
  Co-workers who will assist with Flu-FIT implementation and delivery
  Patients who will participate in Flu-FIT
  Others?

## Slide 41: What strategies might you use to communicate with these stakeholders?
Schedule a one-to-one meeting
Post information on a bulletin board
Include an article in your organization’s newsletter
Create a flyer
Present a brief report at a staff meeting
Gain media coverage (e.g., newspaper, radio, TV)
Post to social media (e.g., Facebook, Twitter, Instagram)
Other?
Notes: Talking Points:
Using same list of audiences from prior slide, talk about channels that might be most effective.

## Slide 42
Understand problem
Establish goals for improvement
Find and Select EBIs
Adapt EBIs
Implement EBIs
Evaluate impact
Engage Stakeholders